## Slide 1: Software Project Management
The main goal of SPM is to enable a group of software developer to work efficiently towards successful completion of the project.
Responsibilities of a Software Project Manager
We can broadly classify the different activities of a project manager into project planning & project monitoring & control activities.
Project Planning
Project Monitoring & Central Activity

## Slide 2
PROJECT Planning - :
        Project planning involves estimating several characteristics
        Of the project & then planning the project activity based on the estimate's mode .Project planning undertaken immediately after the feasibility study & before the requirement analysis specification phase.
Project Monitoring & Control Activity:
        The project monitoring & control activities are undertaken once the development activities start.

## Slide 3: Project Planning
Estimation:
  Cost
  Duration
  Effort
  The effectiveness of all other planning activities such as scheduling and staffing are based on the accuracy of these estimation.
Scheduling
Staffing
Risk Management
Miscellaneous Plans.

## Slide 4
EFFORT ESTIMATION
SIZE ESTIMATION
DURATION ESTIMATION
PROJECT STAFFING
COST ESTIMATION
SCHEDULING

## Slide 5: Metrics for project Size Estimation
The Project size is measure of the problem complexity in terms of the effort and time required to develop the product .
Two Metrics are:
LOC
FP

## Slide 6: Line of Coding (LOC)
LOC gives a numerical value of problem size that can vary widely with individual coding style.
LOC is a measure of the coding activity alone
A good problem size measure should consider the total effort needed to specify, design ,code , test etc;
LOC measure correlate poorly with the quality & efficiency of the code . Larger code size does not necessarily imply better quality or higher efficiency

## Slide 7: Line of Coding (LOC)
LOC metric penalizes use of higher-level programming language , code , reuse etc.
It measures the lexical complexity of a program & does not address the more important but subtle issues of logical or structural complexity
IT is very difficult to accurately estimate LOC in the final product from the problem specification

## Slide 8: Function Point Metric
It can be used to easily estimate the size of a software directly from the specification.
SIZE dependent on the number of functions or feature.
Query Book
Issue Book
Return Book
Book name
Book location
Input Data
Output Data
LAS System

## Slide 9: FP computed in three steps
Compute UFP(Unadjusted Function Point)
UFP is refined
FP is computed by further refining UFP

## Slide 10: UFP
UFP=(No Of inputs)*4 + (Number of Outputs)*5 + (Number Of inquiries)*4 + (Number of files)*10 + (Number of interfaces)*10
No Of Inputs:
The data items name, age, sex, address, phone number etc. are together considered as a single input.
Number of outputs:
The outputs considered refer to reports printed, screen outputs , error message produced etc.
Number of inquiries:
Number of inquiries is the number of distinct interactive queries which can be made by the users.

## Slide 11
Number of files : Each logical files.
Number of interfaces: Data files on tapes, disks , communication links with other systems, etc.

## Slide 12: Refinement of Function point Metric
TYPE | SIMPLE | AVERAGE | COMPLEX | 
INPUT | 3 | 4 | 6 | 
OUTPUT | 4 | 5 | 7 | 
INQUIRY | 3 | 4 | 6 | 
NO . FILES | 7 | 10 | 15 | 
NO. INTERFACE | 5 | 7 | 10 | 

## Slide 13: TCF
Technical Complexity Factor (TCF) is a factor used in software engineering to account for technical considerations when estimating the size of a software project. TCF is part of the Use Case Metrics estimation technique and the Use Case Point (UCP) method, which is used to estimate software development effort.
To calculate TCF, you can:
  Assign a score between 0 and 5 to each of the 13 technical factors listed in a table. A score of 0 means the factor is irrelevant, and a score of 5 means it's essential.
  Multiply each score by the factor's weighted value.
  Add up the results to get the Technical Factor (TF).
  Use the TF to calculate TCF with the formula TCF = 0.6 + (TF/100).
For example, if the relative magnitude of every technical factor is 2, the adjusted sum would be 28. The TCF would then be 0.6 + 0.28 = 0.88.

## Slide 14: TCF
A Technical complexity factor(TCF) for the project is computed and the TCF is multiplied with UFP to yield FP . Albrecht identified 14 parameters that can influence the development effort . Each of these 14 factors is assigned a value from O t0 5.The resulting numbers are summed . Now TCF is computed as (0.65+0.01*DI).As DI can vary from 0 to 70.TCF can vary from 0.65 to 1.35.Finally ,FP is given as the product of UFP and TCF . That is FP=UFP*TCF

## Slide 15: Factors are :
Data communication
Distributed computing
Performance objectives
Operation configuration load
Transaction rate
Online data entry
End user efficiency
On-line update
Complex processing
Logic re-usability

## Slide 16: Factors are :
Installation ease
Operational ease
Multiple sites desire to facilitate change.

## Slide 17: Feature Point Metric
Major shortcoming of function point measure is that it does not take into account the algorithmic complexity of a software.
Feature point metric incorporates algorithm complexity as an extra parameter.
Feature point & function point metrics are language independent & can be easily computed from SRS.

## Slide 18: Software Cost Estimation Techniques
Empirical techniques:
  an educated guess based on past experience.
Heuristic techniques:
  the parameters to be estimated can be expressed in terms of some mathematical expression.
Analytical techniques:
  derive the required results starting from certain simple assumptions.

## Slide 19: Software Cost Estimation Techniques
Empirical techniques:
  Expert Judgement Technique,
  Delphi Cost Estimation.
Heuristic techniques:
  COCOMO.
Analytical techniques:
  Halstead’s Software Science.

## Slide 20: Empirical Estimation Techniques
Based on making educated guess of the project parameters. Prior EXPERIENCE with development of similar product is helpful. Based on common sense.
  Expert judgment Technique :
          This is subject to human error.
          It may still exhibit bias on issues where the entire group of experts may still exhibit may be biased due to reasons such as political consideration.
          It may be dominated by excessively assertive members

## Slide 21: Empirical Estimation Techniques
  Delphi Cost Estimation:
      It is carried out by a team comprising of a group of experts and a coordinator.
        SRS
Coordinator
Expert 1
Expert 2
Expert 3
Estimated Document
Summary Information include any
unusual rational note
Re Estimated Document
Compilation
Final Estimate

## Slide 22: A Heuristic Estimation technique
          COCOMO MODEL
Constructive Cost Estimation Model was proposed by Bohem,1981
Boehm's definitions of organic , semidetached & embedded systems are elaborated as follows :
  Organic : We can consider a development project to be of organic type , if the project deals with developing a well-understood application program , the size of the development team is reasonably small, and the team members are experienced in developing similar types of projects.
  Semidetached: If the development team consists of a mixture of experienced and inexperienced staff.
  Embedded: A development project is considered to be of embedded type , if the software being developed is strongly coupled to complex hardware , or if stringent regulations on the operational procedures exist .

## Slide 23
Time in months
Number of persons working on the project
Person-month curve
PM is considered to be an appropriate unit for measuring effort

## Slide 24: People vs Months
People | Months
50.0 | 1
25.0 | 2
16.7 | 3
12.5 | 4
10.0 | 5
8.3 | 6
7.1 | 7
6.3 | 8
5.6 | 9
5.0 | 10
4.5 | 11
4.2 | 12
3.8 | 13
3.6 | 14
3.3 | 15
3.1 | 16
2.9 | 17
2.8 | 18
2.6 | 19
2.5 | 20

## Slide 25: Basic COCOMO Model
Effort=a1 * (KLOC)a2 PM
Tdev=b1*(Effort)b2 Months
KLOC =Kilo Lines of Code
a1,a2,b1,b2 are constant for each category of software products
Tdev is the estimated time to develop the software
Effort expressed in person month.

## Slide 26: Effort Estimation (Basic COCOMO)
Organic : Effort = 2.4(KLOC)1.05 PM
Semidetached : Effort = 3.0(KLOC)1.12 PM
Embedded = 3.6(KLOC)1.20 PM
Effort Estimation (Detailed COCOMO)
Organic : Effort = 3.2(KLOC)1.05 PM
Semidetached : Effort = 3.0(KLOC)1.12 PM
Embedded = 2.8(KLOC)1.20 PM

## Slide 27: Estimation of development time
Organic : Tdev = 2.5(Effort)0.38 Months
Semidetached : Tdev = 2.5(Effort)0.35 Months
Embedded :Tdev= 2.5(Effort)0.32 Months

## Slide 28
COST : TIME * RATE PER UNIT Rs
Productivity = KLOC / Effort
Average Staff Size : Effort / TDEV (person)

## Slide 29: Ex: Assume that the SIZE of an organic type software product has been estimated to be 32,000 lines of source code .Assume that the average salary of software developers is RS 15,000 per month. Determine the effort required to develop the software product, the nominal development time and cost to develop the product

## Slide 30: Ex :Assume that the SIZE of an organic type software product has been estimated to be 32,000 lines of source code .Assume that the average salary of software developers is RS 15,000 per month. Determine the effort required to develop the software product, the nominal development time and cost to develop the product
From the basic COCOMO estimation formula for organic software:
  Effort = 2.4 * (32)1.05 = 91 PM
  Nominal development Time: 2.5 *(91)0.38 = 14 months
  Cost required to develop the product = 14*15000=
  Rs 210,000.

## Slide 31: Detailed COCOMO
BASIC COCOMO deals with only the program size
Other parameters should be considered to get accurate cost
COST DRIVER is introducing to refine initial cost
A set of 15 cost drivers depending on different parameters
COST driver can be classified
Product
Computer
Personal
Development Environment

## Slide 32: Complete COCOMO
Previous COCOMO models considers homogeneous entity
Large Systems divided into different subsystems; Those are may be mixture of organic ,semidetached & embedded
Each subsystem requires individual cost estimation ,effort, development time manipulation.

## Slide 33
COST DRIVER :
COST DRIVER | RATING |  |  |  | 
 | VERY LOW | LOW | NOMINAL | HIGH | VERY HIGH
PRODUCT ATRIBBUTES |  |  |  |  | 
RELY,REQUIRED RELIABILITY | 0.75 | 0.88 | 1 | 1.15 | 1.4
DATA,DATABSE SIZE |  | 0.94 | 1 | 1.08 | 1.16
CPLX,PRODUCT COMPLEXITY | 1.7 | 0.85 | 1 | 1.15 | 1.3
COMPUTER ATTRIBUTES |  |  |  |  | 
TIME,EXECUTION TIME |  |  | 1 | 1.11 | 1.3
STOR,MAIN STORAGE CONST |  |  | 1 | 1.06 | 1.21
VITR,VIRTUAL MACHINE VOLATILITY |  | 0.87 | 1 | 1.15 | 1.3
TURN,TURNAROUND TIME |  | 0.87 | 1 | 1.07 | 1.15
PERSONAL ATTRIBUTES |  |  |  |  | 
ACAP,ANALYST CAPABILITY | 1.46 | 1.19 | 1 | 0.86 | 0.71
AEXP,APPLICATION EXP | 1.29 | 1.13 | 1 | 0.91 | 0.82
PCAP,PROGRAMMER CAPA | 1.42 | 1.17 | 1 | 0.86 | 0.7
VEXP,VIRTUAL MACHINE EXP | 1.21 | 1.1 | 1 | 0.9 | 
LEXP,PROG. LANGAGE EXP | 1.14 | 1.07 | 1 | 0.95 | 
PROJECT ATTRIBUTES |  |  |  |  | 
MODP,MODERN PROG. PRACTICES | 1.24 | 1.1 | 1 | 0.91 | 0.82
TOOL,USE OF SW TOOL | 1.24 | 1.1 | 1 | 0.91 | 0.83
SCHED,DEVELOPMENT SCHEDULE | 1.23 | 1.08 | 1 | 1.04 | 1.1

## Slide 34
PHASE-WISE DISTRIBUTION OF EFFORT |  |  |  | 
PHASE | SIZE |  |  | 
 | SMALL(2 KLOC) | INTERMEDIATE(8 KLOC) | MEDIAM(32 KLOC) | LARGE(128)
PRODUCT DESIGN | 16 | 16 | 16 | 16
DETAILED DESIGN | 26 | 25 | 24 | 23
CODE & UNIT TEST | 42 | 40 | 38 | 36
INTEGERATION & TEST | 16 | 19 | 22 | 25
The final effort estimated by multiplied the initial estimated by the EAF. E = EAF * Ei

## Slide 35
Problem 1: Let us assume that the software product is containing an estimated to be 62000 lines of source code. The average salary of software engineers is Rs 20000/- per month. The effort & cost of the development can be?
183, 3,60000/-
Problem 2: A project has 400 KLOC. Estimate the effort and development time for each of the three modes.
Problem3 : A project size of 200 KLOC is to be developed .Software development team has average on similar type of products. The project schedule is not very high. Calculate the development time, average staff size & productivity of the project.

## Slide 36
Q. The value of size in KLOC and different cost drivers for a project are given :
              Size=200 KLOC
              Cost Driver :
                Software reliability : 1.15
                Use of software tools : 0.91
                Product complexity : 0.85
                Execution time constraint :1.00
Calculate the effort for organic COCOMO model

## Slide 37
The value of size in KLOC and different cost drivers for a project are given :
              Size=200 KLOC
              Cost Driver :
                Software reliability : 1.15
                Use of software tools : 0.91
                Product complexity : 0.85
                Execution time constraint :1.00
Calculate the effort for organic COCOMO model
Effort Adjustment Factor (EAF) is EAF = 1.15 * 0.91*0.85*1.00 = 0.8895
E = 3.2 * (200)^1.05 * 0.8895 = 742 PM Ans.

## Slide 38
Q. Find out the individual effort in PM unit for Basic design , Detailed design ,C&U Testing, and Integration For Office Automation if it has four major modules :
Data Entry : 0.6 KLOC
Data Update : 0.6 KLOC
Query:0.8 KLOC
Report : 1 .0 KLOC
By interpolation It is given that efforts are distributed as follow :
Basic Design=16%,
Detailed Design=25.83%,
C&U Testing :41.66%,
Integration=16.5%
Cost driver :
Complexity: high(1.15)/Storage:High(1.06)/Experience:low(1.13)/Programming Capability: low(1.17)./All other factors are nominal.

## Slide 39
Now we can consider OAS as organic system :
So, Ei= 3.2*3^1.05 =10.14 PM, EAF= 1.15*1.06*1.13*1.17 = 1.61
E = 1.61* 10.14 =16.3 PM
Now total size is 3KLOC. It is belonged between small & intermediate Size.
By interpolation we can find out the phase distribution :
Design=16%,Detailed Design=25.83%,C&U Testing :41.66%,Integration=16.5%
Effort estimates
Design=16%*16.3=2.6 PM, Detailed Design=25.83% * 16.3 = 4.2 pm, C&U Testing :41.66% * 16.3 = 6.8 pm, Integration=16.5%* 16.3 = 2.7 pm.

## Slide 40
Problem :Suppose a system for office automation to be designed . There are 4 modules in the system: data entry , data update , query & report generator . The project falls in the organic category. The effort of the different modules are in the ratio 2:2:3:5 and the total size of the project is 6 KLOC in the 1st year and 2 KLOC in the 2nd year. The cost driver are :
Complexity High :1.5
Storage High: 1.06
Experience High :1.13
Program Ability : 1.17
Obtain effort estimates for entire project for different phases in 2 year.

## Slide 41: Advantages of COCOMO
Easy to verify the working involved in it.
Cost drivers are useful in effort estimation as they help in understanding the impact of different parameters involved in the cost estimation.
Efficient and good for sensitively analysis.
Can be easily adjusted according to the organization needs & environment

## Slide 42: Disadvantages of COCOMO
Difficult to accurately estimate size in the early phase of the project.
Vulnerable to misclassifications of project type
Success depends on calibration of the model according to the needs of the organization .This is done during using historical data ,which is not always available
Exclude overhead cost , travel cost & other incidental cost.

## Slide 43: COCOMO II
As the project progress through these models can be applied at the different stages of the same project :
  Application composition: This model as the name suggests, can be used to estimate cost for prototyping.
  Early design : This provides cost estimation during detailed design & coding stages.
  Post architecture stage: this provides coat estimation during detailed design& coding stages.

## Slide 44: Halstead's Software Science
An analytical technique to estimate:
  size,
  development effort,
  development time.

## Slide 45: Halstead's Software Science
Halstead used a few primitive program parameters
  number of operators and operands

## Slide 46: Halstead's Software Science
Derived expressions for:
  Program length, (N=N1+N2)[Total]
  Program vocabulary, (η=η1+η2)[unique]
  Program volume, (V=Nlog2η)
  Potential minimum volume, (V*=(2+η2)log2(2+η2)
  Language level, (L=V*/V)
  Effort, (E=V/L) and
  Development time (T=E/S).[where S is the speed of mental discriminations , It is developed from psychological reasoning , recommended value is 18]

## Slide 47: Halstead's Software Science
Operators???
Operands???

## Slide 48: Halstead's Software Science
Let us consider the following C program:
main()
{
int a, b, c, avg ;
scanf(“%d %d %d”, &a,&b,&c);
avg=(a+b+c)/3;
printf(“avg= %d”, avg);
}

## Slide 49: Halstead's Software Science
Let us consider the following C program:
int sort (int x[],int n)
{
int i, j, temp, k ;
if(n<2) return 1;
for(i=2;i<n;i++)
{
k=i-1;
for(j=1;j<=k;j++)

## Slide 50: Halstead's Software Science
if(x[i]<x[j])
{ temp=x[i];
x[i]=x[j];
x[j]=temp;
}
}
return 0;
}

## Slide 51: Halstead’s Software Science :An Analytical Technique
Find out the program length & volume of the given program:
main()
{
int a,b,c,avg;
scanf(“%d%d%d”,&a,&b,&c);
avg=(a+b+c)/3;
printf(“avg = %d”,avg);
}
Unique operators : main(),(),{},int, scanf, &, ” ,” ,”;” ,=,+,/, printf = 12 (Number of Operators)
Unique operand = a,b,c,&a,&b,&c,a+b+c,avg,3,”%d..%d”,” avg=%d”, =11(Number of Operands)

## Slide 52
n1=12,n2=11
Estimated length =n1logn1+n2logn2= (12*log2 12 +11 * log211) = 81
Volume = Length * log2(23)=81 * 4.52 =366
Length = N= n1 *log2n1 +n2 * log2n2
Volume= N * Log2 (n1+n2) [ where n1+n2 = program vocabulary]

## Slide 53: Staffing level estimation
Once the effort required to develop a software has been determined, it is also need to determine Staffing requirement for the project.
Norden’s Work
Rayleigh Curve
Effort per unit Time
Time td
E = ( K/t2d ) *t * e ((-t)2/2t2d)

## Slide 54: Putnam’s Work
      m(t) = 2K*a*t*(exp-at2)
      K : Total effort //Total cost
      a: : Acceleration factor [ a=1/2t2d]
      td : development time // delivery time
      m(t) = (K/t2d)*te(-t2/2t2d) // number of persons at any time t (in years)
      m0 = K/(td √e) // No of person at the peak

## Slide 55: Consider a large-scale project for which the manpower requirement is K=600 PY and the development time is 3 years 6 months 1. Calculate the peak manning & peak time 2.What is the manpower cost after 1 year and 2 months. 3. Calculate the difficulty & manpower build up.

## Slide 56
We know td = 3 years and 6 months = 3.5 years
Now mo = K/td√e = 600/(3.5*1.648) = 104 persons
We know
y(t) =K[1-e-at2 ]
t = 1 year & 2 months = 1.17
a = 1/(2td2 ) = 0.041
Y(1.17) = 600[1- e -0.041(1.17)2]
= 32.6 PY

## Slide 57
Difficulty D = K / td2
= 600 / (3.5)2
= 49 persons/ year
Manpower Build up =
D0 = K/td3
= 600 / (3.5)3
= 14 persons/ year 2

## Slide 58: Putnam’s Observation:
Small no of engineers at the beginning of the project
For planning & specification
Project progresses so more detailed work is required & therefore more engineers are required
After implementation & unit testing the no staff size falls
The team size always follows Rayleigh-Norden curve
Constant level of manpower throughout the project is wastage of effort & time increasing factor

## Slide 59: Our observation
40% of the Rayleigh curve left of td & 60% is right to td . This implies that the ratio of the effort required to develop the product to its maintenance effort is approximately 40:60 .

## Slide 60: Scheduling :
To schedule the project activities
  Identify all the tasks needed to compute the project.
  Breakdown the large tasks in the small activities
  Determine the dependency among different activities
  Establish the most likely estimates for the time durations necessary to complete the activities.
  Allocate resources to the activities
  Plan the storing & ending dates for various activities.
  Determine critical path.

## Slide 61: Work breakdown structure (WBS)
It is used to decompose a given task , set recursively into small activities.
MIS
Design
Requirements Specification
Code
Test
Document
GUI Part
DataBase Part
Database Part
GUI Part

## Slide 62: Activity Networks
WBS representation of a project is transformed into an activity network by representing the activities identified in WBS along with their interdependencies .An activity network shows the different activities making up a project ,their estimated durations and interdependencies .Each activity is represented by a rectangular node and the duration of the activity is shown along side each task.

## Slide 63: Activity Networks
Specification
15
Write user Manual 60
Design GUI Part 30
Design Database Part 45
Code Database Part 105
Code GUI part 45
Integration & Test 120
Finish o

## Slide 64: Critical Path Method(CPM)
MT : To compute the project is the maximum of all path from start to finish
ES: It is the maximum of all paths from the start to this task
LS : it is the difference between MT and the maximum of all paths from this task to the finish
EF :It is the sum of the earliest start time of the task and the duration of the task.
LF: It is obtained by subtracting maximum of all paths from this task to finish from MT (exclude its duration).
ST: Slack time can be written as LF – EF .
Critical task is one with zero slack time.
A path from the start node to finish ,containing only critical task is called critical path.

## Slide 65
For MIS | Duration | ES | EF | LS | LF | ST
SP | 15 | 0 | 15 | 0 | 15 | 0
DD | 45 | 15 | 60 | 15 | 60 | 0
DG | 30 | 15 | 45 | 90 | 120 | 75
CD | 105 | 60 | 165 | 60 | 165 | 0
CG | 45 | 45 | 90 | 120 | 165 | 75
IT | 120 | 165 | 285 | 165 | 285 | 0
WUM | 60 | 15 | 75 | 225 | 285 | 210
MT =285

## Slide 66: Gantt Chart
It is mainly used to allocate resources to activities . Like Staff ,Hardware , Software etc.
Gantt chart is a special type of bar chart where each bar represent an activity.
It is the special type of bar chart where each bar represents the activity.

## Slide 67: Gantt Chart
Jan1 JAN15 MARCH15 APR1 JULY15 NOV15
SP
DESIGN GUI PART
CODE DB PRT
INTEGRATE & TEST
CODE GUI PRT
DESIGN DB PART
WRITE USER MANUAL

## Slide 68: PERT CHART
Project evaluation & review technique
The boxes of PERT charts are usually annotated with the pessimistic, likely & optimistic estimates for every task.
There is not one but many critical paths, depending on the permutation of estimates for each task.
Gantt chart is helpful in planning the utilization of resources but PERT is useful for monitoring the timely progress of activity.

## Slide 69: Activity Networks
Specification
12, 15,20
Write user Manual 50,60,70
Design GUI Part 24,30,38
Design Database Part 40,45,60
Code Database Part 95 ,105,120
Code GUI part 38,45,52
Integration & Test 100,120,140
Finish o

## Slide 70: Questions

## Slide 71: What are the main goals of Software Project Management (SPM)? What are the two main responsibilities of a Software Project Manager? What activities are involved in project planning in software project management? What are the key components of effort estimation in project planning? What metrics are used for project size estimation? What is LOC, and why is it used as a metric in software development? What are some limitations of using Lines of Code (LOC) as a metric for software projects? How is the Function Point (FP) metric calculated in software project management? What are the steps to compute Unadjusted Function Points (UFP)? What is the Technical Complexity Factor (TCF), and how does it influence the Function Point (FP) calculation?

## Slide 72: What are some examples of factors that influence the Technical Complexity Factor (TCF)? What is the Feature Point Metric, and how does it differ from the Function Point Metric? What are the three main types of software cost estimation techniques? Describe the Empirical Estimation Techniques in software cost estimation. What is the Delphi Cost Estimation technique, and how does it work? What is the COCOMO model, and what are its different types? Explain the difference between Organic, Semidetached, and Embedded types of software projects in the COCOMO model. How is effort calculated using the Basic COCOMO model for different project types? What is the Effort Adjustment Factor (EAF), and how is it applied in the COCOMO model? What are the advantages and disadvantages of using the COCOMO model in software cost estimation?